# Logframe matrix

|  | Results chain | Indicators |  | Baseline 2017 | Current value 2017 | Targets 2020 | Sources and means of verification |  | Assumptions |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Overall objective: Impact | To strengthen the competitiveness of Bambam Ltd. | %20 increase in profit |  | 125,000 EUR Annual Net Profit | 125,000 EUR Annual Net Profit | 150,000 EUR Annual Net Profit | Annual Accounts |  |  |
| Specific objective(s): Outcome(s) | - To put sustainable farming practices in application, in 18 months, through introduction of energy efficiency. - To introduce quality standards and food safety. - To introduce information technology. | - Generation of electricity need of agricultural production through renewable energy within 18 months. - Obtained globally accepted certification for food safety, environmental management, quality management, occupational health and safety within 18 months. - Business management software and marketing plan set up within 18 months. |  | - No electricity from renewable energy sources - No certification - No Business management software no marketing plan | - No electricity from renewable energy sources - No certification - No Business management software no marketing plan | - All required energy is generated through renewable sources - 5 Globally recognised certificates received - Business management software and management plan in use | - Project progress report. - Energy utility reports and bills - ISO 9001, OHSAS 18001, ISO 14001 & HACCP standards certificate. - Inspection reports and risk assessment of the production activities. |  | - Local norms promote dissemination of sustainable farming applications in rural areas. - Consumer interest in organic agricultural products. |
| Outputs | - To commission a 150 Kw capacity solar electricity generation system. - 100% of the energy demand of the facility generated by renewable energy sources. - Increased quality of products. - Set up of business management software of the firm - Increased company visibility in the market. | - A 150 Kw capacity solar power system installed and commissioned. - Decrease 100% of network electricity usage. - ISO 9001, OHSAS 18001, ISO 14001 & HACCP standard certificates acquired. - 11 personnel received training on food safety, environmental management, occupational health and safety and quality management. - Accountancy/business management software procured and installed. - 4 personnel received training on the operation of the system - Website developed in two languages. - Delivery of promotion ceremony. |  | - 10,000 EUR average monthly electricity usage - No certification - Low capacity of the personnel - No software - No website | - 10,000 EUR average monthly electricity usage - No certification - Low capacity of the personnel - No software - No website | - 100 EUR/monthly - 5 Globally recognised certificates received - 11 personnel received training - Business management software and management plan in use - 4 personnel received training on accounting software. | - Supply contracts signed, invoices paid to the suppliers. - ISO 9001, OHSAS 18001, ISO 14001 & HACCP standard certificates. - Training documents and training participant lists. - Website. - Pictures of the ceremony. |  | - Suppliers and service providers willing to participate in the tender. - Customers of the firm will adopt their practices to business management software of the firm. |
| Activities | - Procurement and commissioning of the solar power generation system. - Procurement of ISO 9001, OHSAS 18001, ISO 14001 & HACCP standards certificates - Procurement of accountancy/business management software. - Procurement of website design and development. - Visibility activities - Interim Procurement, interim and final reporting activities. |  | Means: - Equipment: Solar energy system - Service tender - Visibility actions: Open day event. Costs - Equipment/Supplies: € 386,790.00 - Other costs/services: €7,390.00 - Other: €42,245.00 - Administrative costs: €5,804.45 TOTAL: €442,229.45 |  |  |  |  | - Unfavourable Weather conditions - Change in the regulation - No offers received for tenders |  |